## Sheet1
Project ID | Project Name | Agency | State | Sector | Project Status | Start Date | Original/Target DoC | Revised DoC | Original Cost (Rs. Crore) | Revised Cost (Rs. Crore) | Cumulative Expenditure (Rs. Crore) | Monthly Expenditure | Physical Progress (%) | Financial Progress (%) | Month & Year | Delay Months | Delay Reason | Actual Completion Date | Actual Final Expenditure
701105 | Goa Airport Terminal Building Extension Project | Airport Authority of India [AAI] | Goa | Civil Aviation | Ongoing | 12/2019 | 12/2021 | 04/2026 | 255.69 | 255.69 | 161.06 | 3.2 | 63 | 63 | July 2026 | 52 | Design revision and slow mobilization by contractor
701263 | Rajasthan Refinery Project | HPCL Rajasthan Refinery Limited [HRRL] | Rajasthan | Petroleum | Ongoing | 01/2018 | 10/2022 | 12/2026 | 43129 | 72937 | 58240.5 | 820 | 82.5 | 79.8 | July 2026 | 50 | Delay in equipment delivery from foreign vendors and Covid lockdown